## Project Info (hidden)
Complexity characteristics questionnaire
Consider one of your most recently completed projects, for which data will be collected, and reply to the following questions
Project Title:
Duration: | (please state if in wks or mths)
Initial Cost Estimate: |  | Current Anticipated Final Cost:
Initial Start Date (Baseline): |  | Current Start Date:
Planned Completion Date (Baseline): |  | Expected Completion Date:
Comments on Starting Conditions:

## Qstnr-Conditional
Vathmos
Characteristic: C1) Autonomous agents.
Each and every individual contributing to a project is considered to be an autonomous agent and regarded as equally valuable in the operation of the system.
Q_SLC1Sel:
Down to what level is the selection of the project team members going? | worksheet SLC1Sel | [5 empty] | 15
Q_SLC1Str:
Down to what level do you (or ask for) define the structure of the team? | Use scales and ranking in worksheet SL .ppt and enter selection in the adjecent box |  |  |  | L1 | 10 | 10
Q_SLC1Mng:
a) To what extend does your management style accommodate for Autonomous Agents? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) What management style is rolled down the project levels? | worksheet MngtStl | [5 empty] | 50
Characteristic: C2) Instability
Stepped evolution(s) or catastrophes do occur in projects. Attractors (see definition) appear (currently unintentionally) and become system parameters and which will attract and avoid chaotic behaviour of the project system.
Q_SLC2Sel:
Do you allow for the transfer of responsibility to more appropriate people? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLC2Str:
Do you identify these roles in the project structure, or the processes? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLC2Mng:
Does your management style accommodate for the apportionment of authority to experts? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Characteristic: C5) Attractors
Simple systems (individuals) come together and many times self-organise to form more complex systems which are pulled by the presence of the dynamic attractors of the moment.
Further explanation: The top-2-bottom hierarchical structure allows only for the identification of lines of responsibility. However, complexity (defined as the study of interconnections of systems) identifies as one of the characteristics the need/existence of attractors, which are / could be construed as individuals who when required become the poles of attraction. So we have individuals, that could easily not be the line managers, who because of their capabilities, abilities, behavioural attributes are assigned to be ‘attractors’ is a certain situation arises.
Q_SLC5Sel:
Have you planned for the attractors to be able to self-organise the teams around them? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLC5Str:
a) Do you allow for self-organisation and the existence of attractors in you project? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) Down to what level have you allowed for self-organisation and the existence of attractors in your project? | Use scales and ranking in worksheet SL .ppt and enter selection in the adjecent box |  |  |  | L1 | 10 | 10
Q_SLC5Mng:
To what extend does your management style accommodate for the existence of attractors? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Characteristic: C4) Non-linear
Individuals seen as complex systems that work in a project and outperform themselves when faced with challenging conditions and under a good environment encouraging team work, understanding and noticing individuals’ contribution, establishing team work rather than group work or individualistic behaviour.
Q_SLC4Sel:
Down to what level do you select or train individuals to be able to perform in a team environment? | Use scales and ranking in worksheet SL .ppt and enter selection in the adjecent box |  |  |  | L1 | 10 | 10
Q_SLC4Str:
Does your project structure allow for the building of teamwork and down to what level? | Use scales and ranking in worksheet SL .ppt and enter selection in the adjecent box |  |  |  | L1 | 10 | 10
Q_SLC4Mng:
a) Does your management style accommodate the understanding of individuals as complex systems and enabling teamwork? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) What management style do you follow to allow for the building of a team environment throughout the project organisation? | go to worksheet MngtStl | [5 empty] | 30
Characteristic: C3) Non-equilibrium
The various ‘pulls’ (contractual, behavioural, stakeholder influences, company politics, and management pressures, to mention but a few) that occur in projects from the multiple contributors which, depending on the situation, will establish semi-stable modes with ‘players’ (attractors) who will attempt to influence the project at the opportune moment.
Q_SLC3Sel:
Do you select individuals to perform the role of attractor? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLC3Str:
a) Do you identify / establish attractors within the project structure? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) Down to what level do you introduce attractors? | Use scales and ranking in worksheet SL .ppt and enter selection in the adjecent box |  |  |  | L1 | 10 | 10
Q_SLC3Mng:
To what extend does your management style accommodate for the existence of attractors? | No / Does not | Not always | Sometimes | Most times | Yes
| TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Go to
Go to
Go to
Go to
Go to
Go to
Go to
Go to

## Qstnr-Developmental
Characteristic: D1) Co-evolution
The parts are regarded as evolving in conjunction with each other in order to fit into a wider system environment. This is self-evident in the Project Management world.
Further explanation: Individuals within teams and teams within projects co-evolve and initially attempt to understand each other in order to understand the requirements and fit into the wider project environment
Q_SLD1Sel:
a) Do you take any measures to allow for this to happen, or do you let the teams work this out? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | FALSE | FALSE | TRUE | FALSE | FALSE |  | 50
b) What measures do you take to allow for co-evolution when selecting the team members? |  | worksheet SLD1bSel | [5 empty] | 1.5873
Q_SLD1Str:
What level of flexibility do you instil in the project structure to allow for co-evolution of the teams? |  | worksheet SLD1Str | [5 empty] | 0
Q_SLD1Mng:
a) Does your mngt style accommodate for the parties in the project to evolve with each other? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) What management style do you follow to allow for the co-evolution of the teams? |  | go to worksheet MngtStl | [5 empty] | 30
Characteristic: D2) Self-modification
Individuals and teams form and change their associations as they are evolving and learning during the project life-cycle.
Q_SLD2Sel:
Is there a managed process where individuals and teams are introduced, and then continuously educated around the project and its outcome? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLD2Str:
a) Is this beneficial for the project structure or not? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) What steps do you take to enable / restrict this in the project structure? |  | worksheet SLD2bStr | [5 empty] | 1.5873
Q_SLD2Mng:
a) To what extend does your mngt style accommodate for managing and coordinating self-modification of individuals and teams through learning? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) What management style do you follow to allow / support the self-modification of the teams? |  | go to worksheet MngtStl | [5 empty] | 50
Characteristic: D3) Self-reproduction
The structure is set up to be the same throughout the project - cloned/copied, despite the fact that different teams may require different organisational structure. Similarly the Mngt style is copied/imposed throughout.
Q_SLD3Sel:
What actions are taken to promote good practice, etc. |  | worksheet SLD3Sel | [5 empty] | 5.8824
Q_SLD3Str:
Do you vary the project organisation structure to fit the project stage, or is does this vary for each team and the work req'd by the team? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLD3Mng:
Is the management style the same throughout the management level on your project? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | FALSE | FALSE | TRUE | FALSE | FALSE |  | 50
Characteristic: D4) Downward Causation
The existence and skills (including characteristics) of individuals and teams within the project are affected by higher level systemic features of the whole.
Further explanation: A number of structures that are set up at project level that indicate the systemic features of the project affect the existence, the properties / requirements of the project parts themselves. Therefore the standard project management structures, WBS, OBS, CBS, etc. as well as the informal project structures (everyday communication, etc.) affect the existence and input by individuals and teams.
Q_SLD4Sel:
a) Is the selection process affected by the systemic / project features? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) If yes is this followed / considered throughout the project life-cycle or is it taken for granted? |  | No | Not always | Initially | Most times | Continously
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
c) How do you instigate/confirm or carry out the selection process based on the project structures (and which ones)? |  | worksheet SLD4cSel | [5 empty] | 10
Q_SLD4Str:
Down to what organisational level do the standard project structures cascade? |  | go to worksheet SLD4Str and worksheet SL .ppt | [5 empty] | 10
Q_SLD4Mng:
The management style affects implementation of processes and structures. What management style do you implement to accommodate the effect of downward causation? |  | go to worksheet MngtStl | [5 empty] | 30
Characteristic: D5) Mutability
It is typical of random mutations to occur in Projects. Project Management has to identify and manage them.
Further explanation: Considering the ‘individual’ as a system, it is highly likely that random internal changes will occur during the life cycle of the project and these will have an effect on the project through the individual’s performance. These internal changes could be beneficial or detrimental and could be caused by either internal, to the project, reasons (e.g. team members’ behaviours), or the individual’s employer (e.g. promotion or demotion), or personal. Perhaps these changes are / could occur at a macro – project unconscious - level, or even a micro – deliberate – level. It is obvious that beneficial random internal changes will improve the individual’s performance, whereas detrimental random internal changes will reduce performance. And whereas beneficial changes could be management led, detrimental changes could remain esoteric and could take longer to be recognized.
Q_SLD5Sel:
a) Do you consider the effects of random changes on team members |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) What measures do you take to minimise, or maximise, the effect(s)? |  | worksheet SLD5bSel | [5 empty] | 0
Q_SLD5Str:
a) Do you consider the effects of random changes on project structure |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) What measures do you take to minimise, or maximise, the effect(s)? |  | worksheet SLD5bStr | [5 empty] | 0
Q_SLD5Mng:
Do you consider the effects of random changes on the management style and what measures do you take to minimise, or maximise, the consequence(s)? |  | worksheet SLD5Mng | [5 empty] | 30
Characteristic: D6) Non-uniform
The individual parties evolve separately and give diversity in projects. This again has to be identified and managed rather than controlled and stopped.
Further explanation: Each person brings its own attributes to the project at the level it operates. The more specialist the level the more autonomy the individual or the team gets thus giving diversity in the rule. As personnel moves from project to project and as all influences from the various factors affect the individual(s) the individuals become carriers and evolve as they move along. No project is the same and no individual can keep on doing the same thing. Individuals evolve through the project life-cycle and through the projects giving diversity in rule or task space. This diversity improves the outcome, as the individual(s) are attempting to achieve a higher status, or benefit.
Q_SLD6Sel:
Do you encourage individuals to diversify in your project? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLD6Str:
Does your project structure encourage diversity? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLD6Mng:
a) Does your management style accommodate for diversity? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) What management style do you follow to encourage diversity? |  | go to worksheet MngtStl | [5 empty] | 30
Characteristic: D7) Emergence
This again is the power of the whole delivering a lot more than the individual parties to the project. The usual 2+2=5. The project takes from each part and combines all properties to produce a holistic system that will deliver the project.
Q_SLD7Sel:
a) When selecting team members do you consider the emergence characteristic? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) How do you combine individuals' characteristics to create an overall emergence? |  | worksheet SLD7bSel | [5 empty] | 0
Q_SLD7Str:
Do you accommodate for emergence in your project structure? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLD7Mng:
a) To what extend does your management style accommodate for individuals and teams coming together to perform as a whole? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) What management style do you implement to encourage emergence? |  | go to worksheet MngtStl | [5 empty] | 30
Characteristic: D8) Phase changes
As far as the individual is concerned this characteristic highlights the importance of feedback processes for their career development. These phase changes / sudden jumps, depending on the approach taken, could have a detrimental or beneficial influence in the individuals’ ‘properties’ attributes. These could either be the standard phase changes that are based on feedback to higher management levels, or even within the standard PM processes that could lead to the sudden jumps described by this property.
Q_SLD8Sel: | 1st Part |  |  |  | 2nd Part
Do you have project related performance feedback to the individuals in your team and are you requesting the other project members to do the same? |  | Yes | No |  | Yes | No | 0 | 0
Q_SLD8Str: |  | FALSE | TRUE |  | FALSE | TRUE
Does your project structure accommodate for changes which are a consequence of feedback mechanisms, (incl. suppliers performance feedback?) |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLD8Mng:
a) Does your management style accommodate for feedback to individuals and teams in order to enable phase-changes? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) What management style do you implement to encourage the set up and running of feedback processes? |  | go to worksheet MngtStl | [5 empty] | 30
Go to
Go to
Go to
Go to
Go to
Go to
Go to
Go to
Go to
Go to
Go to
Go to
Go to
Go to
Go to
Go to

## Qstnr-Behavioural
Characteristic: B1) Unpredictability
This represents the importance of the initial project conditions which if not managed appropriately could lead to chaotic conditions occurring later on the projects (see also pathogens and incubation period, IJPM ref. needed here).
Q_SLB1Sel:
How frequently do you inform (and carry out throughout the duration) project team members and down to lowest level? | Quarterly briefings | Monthly briefings | Weekly briefings | Project Induction | Team Induction | Task Induction | 90
| FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | 0
Q_SLB1Str:
Does the project structure have the flexibility to accommodate changes due to unpredictability? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLB1Mng:
How does your management style change from one stage to the next the initial stages of the project? |  | worksheet SLB1Mng | [5 empty] | 30
Characteristic: B2) Non-standard
Each system that comes to the project will self-organise dynamically with the other project systems and change from its initial homogeneous status.
Further explanation: Complexity requires for systems to have the characteristic of ‘non-standard’ in order to be able to evolve from homogenous systems into dynamic self-organised ones. Each individual (or team) that will come to the project (as a homogenous system) will dynamically develop self-organising structures in order to adjust/adapt to the environment. It could also be said that members of project teams should possess the characteristic of non-standard, which means that they should be able to evolve from homogenous ones into self-organising in order to adapt to the project environment.
Q_SLB2Sel:
a) Do you consider the characteristic of 'non-standard' when you select the project team members? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) How do you do this so that they can adapt to the new project environment and self organise? |  | worksheet SLB2bSel | [5 empty] | 1.5873
Q_SLB2Str:
Do you support this evolutionary structure within your project structure? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Q_SLB2Mng:
Does the management style allow for the flexible approach required? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Characteristic: B3) Undefined values
Identifying the system’s/project’s interfaces with the environment as the external stakeholders (re. W. Hughes 11 external factors see CME paper & my further thoughts on this subject) this characteristic identifies the need for the evolution of the interfaces as the project progress. The complexity characteristic confirms the need for specifying the interfaces and the evolution of appropriate strategies. It represents the effect of the Undefined values on the system/project.
Further explanation: Regarding selecting the team members, and in particular for several roles within the team, the influencing factor of the project interfaces should identified and introduced in the selection criteria process. These individuals should be able to act as attractors when the interfaces are specified and should be supporting the process. They are the project agents who work with the team to delineate the Undefined values.
Q_SLB3Sel:
a) Does your company, during the project team selection process, identify the effect of interfaces on the project against specific roles? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
b) Do you include specific criteria in the selection process? | Yes | worksheet SLB3bSel |  |  |  |  | No | 0
Q_SLB3Str: | FALSE | [5 empty] | TRUE
Down to what organisational level does training on the influence and management of interfaces stop? |  | Use scales and ranking in worksheet SL .ppt and enter selection in the adjecent box |  |  |  | L1 | 10 | 10
Q_SLB3Mng:
How does the management style support the management of interfaces? |  | No / Does not | Not always | Sometimes | Most times | Yes
|  | TRUE | FALSE | FALSE | FALSE | FALSE |  | 10
Go to
Go to
Go to
Go to

## Score (hidden)
AUTAGSLC1Sel | AUTAGSLC1Str | AUTAGSLC1aMng | AUTAGSLC1bMng | INSTSLC2Sel | INSTSLC2Str | INSTSLC2Mng | NnEQUILSLC3Sel | NnEQUILSLC3aStr | NnEQUILSLC3bStr | NnEQUILSLC3Mng | NnLNRSLC4Sel | NnLNRSLC4Str | NnLNRSLC4aMng | NnLNRSLC4bMng | ATTRSLC5Sel | ATTRSLC5aStr | ATTRSLC5bStr | ATTRSLC5Mng | COEVOLSLD1aSel | COEVOLSLD1bSel | COEVOLSLD1Str | COEVOLSLD1aMng | COEVOLSLD1bMng | SLFMODSLD2Sel | SLFMODSLD2aStr | SLFMODSLD2bStr | SLFMODSLD2aMng | SLFMODSLD2bMng | SLFREPRSLD3Sel | SLFREPRSLD3Str | SLFREPRSLD3Mng | DWNCAUSSLD4aSel | DWNCAUSSLD4bSel | DWNCAUSSLD4cSel | DWNCAUSSLD4aStr | DWNCAUSSLD4aMng | MUTABSLD5aSel | MUTABSLD5bSel | MUTABSLD5aStr | MUTABSLD5bStr | MUTABSLD5Mng | NnUNIFSLD6Sel | NnUNIFSLD6Str | NnUNIFSLD6aMng | NnUNIFSLD6bMng | EMERGSLD7aSel | EMERGSLD7bSel | EMERGSLD7Str | EMERGSLD7aMng | EMERGSLD7bMng | PHSCHNGSLD8Sel | PHSCHNGSLD8Str | PHSCHNGSLD8aMng | PHSCHNGSLD8bMng | UNPREDSLB1Sel | UNPREDSLB1Str | UNPREDSLB1Mng | NnSTDSLB2aSel | NnSTDSLB2bSel | NnSTDSLB2Str | NnSTDSLB2Mng | UnDEFVALSLB3aSel | UnDEFVALSLB3bSel | UnDEFVALSLB3Str | UnDEFVALSLB3Mng
15 | 10 | 10 | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 30 | 10 | 10 | 10 | 10 | 50 | 1.5873 | 0 | 10 | 30 | 10 | 10 | 1.5873 | 10 | 50 | 5.8824 | 10 | 50 | 10 | 10 | 10 | 10 | 30 | 10 | 0 | 10 | 0 | 30 | 10 | 10 | 10 | 30 | 10 | 0 | 10 | 10 | 30 | 0 | 10 | 10 | 30 | 0 | 10 | 30 | 10 | 1.5873 | 10 | 10 | 10 | 0 | 10 | 10
[11 empty] | Selecting Team Members | [6 empty] | Structuring Project Team | [6 empty] | Management Style
[5 empty] | Autonomous agents |  |  |  |  | AUTAGSLC1Sel | 15 | [5 empty] | AUTAGSLC1Str | 10 | [5 empty] | AUTAGSLC1aMng | 30
[5 empty] | Instability |  |  |  |  | INSTSLC2Sel | 10 | [5 empty] | INSTSLC2Str | 10 | [5 empty] | INSTSLC2Mng | 10
[5 empty] | Non-equilibrium |  |  |  |  | NnEQUILSLC3Sel | 10 | [5 empty] | NnEQUILSLC3aStr | 10 | [5 empty] | NnEQUILSLC3Mng | 10
[5 empty] | Non-linear |  |  |  |  | NnLNRSLC4Sel | 10 | [5 empty] | NnLNRSLC4Str | 10 | [5 empty] | NnLNRSLC4aMng | 20
[5 empty] | Attractors |  |  |  |  | ATTRSLC5Sel | 10 | [5 empty] | ATTRSLC5aStr | 10 | [5 empty] | ATTRSLC5Mng | 10
[5 empty] | Co-evolution |  |  |  |  | COEVOLSLD1aSel | 25.7937 | [5 empty] | COEVOLSLD1Str | 0 | [5 empty] | COEVOLSLD1aMng | 20
[5 empty] | Self-modification |  |  |  |  | SLFMODSLD2Sel | 10 | [5 empty] | SLFMODSLD2aStr | 5.7937 | [5 empty] | SLFMODSLD2aMng | 30
[5 empty] | Self-reproduction |  |  |  |  | SLFREPRSLD3Sel | 5.8824 | [5 empty] | SLFREPRSLD3Str | 10 | [5 empty] | SLFREPRSLD3Mng | 50
[5 empty] | Downward Causation |  |  |  |  | DWNCAUSSLD4aSel | 10 | [5 empty] | DWNCAUSSLD4aStr | 10 | [5 empty] | DWNCAUSSLD4aMng | 30
[5 empty] | Mutability |  |  |  |  | MUTABSLD5aSel | 5 | [5 empty] | MUTABSLD5aStr | 5 | [5 empty] | MUTABSLD5Mng | 30
[5 empty] | Non-uniform |  |  |  |  | NnUNIFSLD6Sel | 10 | [5 empty] | NnUNIFSLD6Str | 10 | [5 empty] | NnUNIFSLD6aMng | 20
[5 empty] | Emergence |  |  |  |  | EMERGSLD7aSel | 5 | [5 empty] | EMERGSLD7Str | 10 | [5 empty] | EMERGSLD7aMng | 20
[5 empty] | Phase changes |  |  |  |  | PHSCHNGSLD8Sel | 0 | [5 empty] | PHSCHNGSLD8Str | 10 | [5 empty] | PHSCHNGSLD8aMng | 20
[5 empty] | Unpredictability |  |  |  |  | UNPREDSLB1Sel | 0 | [5 empty] | UNPREDSLB1Str | 10 | [5 empty] | UNPREDSLB1Mng | 30
[5 empty] | Non-standard |  |  |  |  | NnSTDSLB2aSel | 5.7937 | [5 empty] | NnSTDSLB2Str | 10 | [5 empty] | NnSTDSLB2Mng | 10
[5 empty] | Undefined values |  |  |  |  | UnDEFVALSLB3aSel | 5 | [5 empty] | UnDEFVALSLB3Str | 10 | [5 empty] | UnDEFVALSLB3Mng | 10
is managed, some more actions are required
is not managed, more actions required

## Charts
Selecting Team Members |  |  |  | Structuring Project Team |  |  |  | Management Style
Characteristic |  | Score | Comment on management of complexity characteristic | Characteristic |  | Score | Comment on management of complexity characteristic | Characteristic |  | Score | Comment on management of complexity characteristic
| Autonomous agents | 15 | is not managed, more actions required |  | Autonomous agents | 10 | is not managed, more actions required |  | Autonomous agents | 30 | is not managed, more actions required
| Instability | 10 | is not managed, more actions required |  | Instability | 10 | is not managed, more actions required |  | Instability | 10 | is not managed, more actions required
| Non-equilibrium | 10 | is not managed, more actions required |  | Non-equilibrium | 10 | is not managed, more actions required |  | Non-equilibrium | 10 | is not managed, more actions required
| Non-linear | 10 | is not managed, more actions required |  | Non-linear | 10 | is not managed, more actions required |  | Non-linear | 20 | is not managed, more actions required
| Attractors | 10 | is not managed, more actions required |  | Attractors | 10 | is not managed, more actions required |  | Attractors | 10 | is not managed, more actions required
| Co-evolution | 25.7937 | is not managed, more actions required |  | Co-evolution | 0 | is not managed, more actions required |  | Co-evolution | 20 | is not managed, more actions required
| Self-modification | 10 | is not managed, more actions required |  | Self-modification | 5.7937 | is not managed, more actions required |  | Self-modification | 30 | is not managed, more actions required
| Self-reproduction | 5.8824 | is not managed, more actions required |  | Self-reproduction | 10 | is not managed, more actions required |  | Self-reproduction | 50 | is not managed, more actions required
| Downward Causation | 10 | is not managed, more actions required |  | Downward Causation | 10 | is not managed, more actions required |  | Downward Causation | 30 | is not managed, more actions required
| Mutability | 5 | is not managed, more actions required |  | Mutability | 5 | is not managed, more actions required |  | Mutability | 30 | is not managed, more actions required
| Non-uniform | 10 | is not managed, more actions required |  | Non-uniform | 10 | is not managed, more actions required |  | Non-uniform | 20 | is not managed, more actions required
| Emergence | 5 | is not managed, more actions required |  | Emergence | 10 | is not managed, more actions required |  | Emergence | 20 | is not managed, more actions required
| Phase changes | 0 | is not managed, more actions required |  | Phase changes | 10 | is not managed, more actions required |  | Phase changes | 20 | is not managed, more actions required
| Unpredictability | 0 | is not managed, more actions required |  | Unpredictability | 10 | is not managed, more actions required |  | Unpredictability | 30 | is not managed, more actions required
| Non-standard | 5.7937 | is not managed, more actions required |  | Non-standard | 10 | is not managed, more actions required |  | Non-standard | 10 | is not managed, more actions required
| Undefined values | 5 | is not managed, more actions required |  | Undefined values | 10 | is not managed, more actions required |  | Undefined values | 10 | is not managed, more actions required

## SLC1Sel
If it is to be used for the whole Project Team including Client’s team
49 | A1 | Only Client Mngt Level | 0% |  | B1 | Only Client from Mngt level down to lowest level | 2.5%
| A2 | Client & Design Mngt Level | 2.5% |  | B2 | Client down to lowest level & Design Mngt Level | 3%
| A3 | Client Mngt Level & Design down to lowest level | 3% |  | B3 | Client down to lowest level & Design down to lowest level | 7.5%
| A4 | Client & Design & Main Contractor Mngt Level | 5% |  | B4 | Client down to lowest level & Design & Main Contractor Mngt Level | 10%
| A5 | Client & Design Mngt Level & Main Contractor down to Site Mngt Level | 7.5% |  | B5 | Client down to lowest level & Design Mngt Level & Main Contractor down to Site Mngt Level | 20%
| A6 | Client & Design Mngt Level & Main Contractor down to lowest level | 20% |  | B6 | Client down to lowest level & Design Mngt Level & Main Contractor down to lowest level | 35%
| A7 | Client Mngt & Design to lowest level & Main Contractor Mngt Level | 12.5% |  | B7 | Client down to lowest level & Design to lowest level & Main Contractor Mngt Level | 30%
| A8 | Client Mngt & Design to lowest level & Main Contractor down to Site Mngt Level | 30% |  | B8 | Client down to lowest level & Design to lowest level & Main Contractor down to Site Mngt Level | 37.5%
| A9 | Client Mngt & Design to lowest level & Main Contractor down to lowest level | 35% |  | B9 | Client down to lowest level & Design to lowest level & Main Contractor down to lowest level | 45%
| A10 | Client & Design & All Contractors’ Mngt Level | 10% |  | B10 | Client down to lowest level & Design & All Contractors’ Mngt Level | 15%
| A11 | Client & Design & Main Contractor & All Contractors’ Mngt Level | 15% |  | B11 | Client down to lowest level & Design & Main Contractor & All Contractors’ Mngt Level | 20%
| A12 | Client & Design Mngt Level & Main Contractor down to Site Mngt Level & All Contractors’ Mngt down to Site Mngt Level | 35% |  | B12 | Client to lowest level & Design Mngt & Main Contractor down to Site Mngt Level & All Contractors’ Mngt down to Site Mngt Level | 40%
| A13 | Client & Design Mngt Level & Main Contractor down to Site Mngt Level & All Contractors’ lowest level | 55% |  | B13 | Client down to lowest level & Design Mngt Level & Main Contractor down to Site Mngt Level & All Contractors’ lowest level | 60%
| A14 | Client & Design Mngt Level & Main Contractor down to lowest level & All Contractors’ lowest level | 65% |  | B14 | Client down to lowest level & Design Mngt Level & Main Contractor down to lowest level & All Contractors’ lowest level | 70%
| A15 | Client Mngt & Design lowest level & All Contractors’ Mngt Level | 40% |  | B15 | Client down to lowest level & Design lowest level & All Contractors’ Mngt Level | 45%
| A16 | Client Mngt & Design lowest level & Main Contractor & All Contractors’ Mngt Level | 50% |  | B16 | Client down to lowest level & Design lowest level & Main Contractor & All Contractors’ Mngt Level | 55%
| A17 | Client Mngt & Design lowest level & Main Contractor down to Site Mngt Level & All Contractors’ Mngt down to Site Mngt Level | 75% |  | B17 | Client to lowest level & Design lowest level & Main Contractor down to Site Mngt Level & All Contractors’ Mngt down to Site Mngt Level | 80%
| A18 | Client Mngt & Design lowest level & Main Contractor down to Site Mngt Level & All Contractors’ lowest level | 80% |  | B18 | Client down to lowest level & Design lowest level & Main Contractor down to Site Mngt Level & All Contractors’ lowest level | 90%
| A19 | Client Mngt & Design lowest level & Main Contractor down to lowest level & All Contractors’ lowest level | 90% |  | B19 | Client down to lowest level & Design lowest level & Main Contractor down to lowest level & All Contractors’ lowest level | 100%
15%
If it is to be used only for Main Contractor’s team and Design team |  |  |  | If it is to be used only for Main Contractor’s team
| C1 | Design & Main Contractor Mngt Level | 7.5% |  | D1 | Main Contractor Mngt Level | 5%
| C2 | Design Mngt Level & Main Contractor down to Site Mngt Level | 15% |  | D2 | Main Contractor down to Site Mngt Level | 15%
| C3 | Design Mngt Level & Main Contractor down to lowest level | 30% |  | D3 | Main Contractor down to lowest level | 25%
| C4 | Design & All Contractors’ Mngt Level | 15% |  | D4 | Main Contractor & All Contractors’ to Mngt Level | 7.5%
| C5 | Design Mngt Level & All Contractors’ down to Site Mngt Level | 17.5% |  | D5 | Main Contractor Mngt & All Contractors’ down to Site Mngt Level | 20%
| C6 | Design Mngt Level & All Contractors’ down to lowest level | 20% |  | D6 | Main Contractor Mngt & All Contractors’ down to lowest level | 30%
| C7 | Design & Main Contractor & All Contractors’ Mngt Level | 15% |  | D7 | Main Contractor down to Site Mngt Level & All Contractors’ to Mngt Level | 35%
| C8 | Design Mngt Level & Main Contractor down to Site Mngt Level & All Contractors’ Mngt down to Site Mngt Level | 35% |  | D8 | Main Contractor down to Site Mngt Level & All Contractors’ down to Site Mngt Level | 40%
| C9 | Design Mngt Level & Main Contractor down to Site Mngt Level & All Contractors’ lowest level | 57.5% |  | D9 | Main Contractor down to Site Mngt Level & All Contractors’ down to lowest level | 65%
| C10 | Design Mngt Level & Main Contractor down to lowest level & All Contractors’ lowest level | 67.5% |  | D10 | Main Contractor down to lowest level & All Contractors’ to Mngt Level | 60%
| C11 | Design to lowest level & Main Contractor Mngt Level | 27.5% |  | D11 | Main Contractor down to lowest level & All Contractors’ down to Site Mngt Level | 85%
| C12 | Design to lowest level & Main Contractor down to Site Mngt Level | 35% |  | D12 | Main Contractor down to lowest level & All Contractors’ down to lowest level | 100%
| C13 | Design to lowest level & Main Contractor down to lowest level | 42.5%
| C14 | Design lowest level & All Contractors’ Mngt Level | 40%
| C15 | Design lowest level & All Contractors’ down to Site Mngt Level | 45%
| C16 | Design lowest level & All Contractors’ down to lowest level | 47.5%
| C17 | Design lowest level & Main Contractor & All Contractors’ Mngt Level | 52.5%
| C18 | Design lowest level & Main Contractor down to Site Mngt Level & All Contractors’ Mngt down to Site Mngt Level | 77.5%
| C19 | Design lowest level & Main Contractor down to Site Mngt Level & All Contractors’ lowest level | 87.5%
| C20 | Design lowest level & Main Contractor down to lowest level & All Contractors’ lowest level | 92.5%
Return 2 Qstnr Conditional
Return 2 Qstnr Conditional

## MngtStl
|  | SLC1bMng | SLC4bMng | SLD1bMng | SLD2bMng | SLD4Mng | SLD6bMng | SLD7bMng | SLD8bMng
P | Management Style | Selection | Selection | Selection | Selection | Selection | Selection | Selection | Selection
| A) Decisions were made after there had been a discussion with the project team – egalitarian approach. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 7
| B) Decisions and actions to be taken were dictated to the project team with no consultation. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
| C) Decisions were made by the teams, who were allowed to manage themselves. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 10
| D) Decisions based on standardised processes, procedures and rules. | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 3
| E) Emphasis was given to perfection and the technical approach rather than an outcome which satisfies the requirements, thus resulting in less delegation and trust on work done by others. | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | 3
| F) The management style varied according to the stages of the project, changing and/or adjusting according to the situation. | TRUE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 5
| G) Emphasis given to systems of control, efficiency and productivity. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
| H) Emphasis was given to project team members’ well-being, their involvement and development rather than your own career progression. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 7
| J) Emphasis was given to the medium to longer term objectives of the organisation, rather than the immediate needs of the client. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 3
|  | 5 | 3 | 3 | 5 | 3 | 3 | 3 | 3
Back 2 Qstnr Conditional
Back 2 Qstnr Development

## SLD1bSel
A1 | A2 | A3 | A4 | B | C
Question SLD1bSel
Selection | [13 empty] | 0.015873
A. Individuals are asked to participate in:
A.1 Induction | [13 empty] | TRUE | 1
A.2 Workshops | [13 empty] | FALSE
A.3 Lunch & Learn sessions | [13 empty] | FALSE
A.4 Weekly combined talks / meetings | [13 empty] | FALSE
B. Establishing roles which will promote and support co-evolution throughout the duration of the project. | [13 empty] | FALSE
C. Selecting individuals that can operate flexibly in a changing environment | [13 empty] | FALSE
1
Combination | [5 empty] | Score
A1 | [5 empty] | 1.587% | 1 | 0 | 0 | 0 | 0 | 0 | 1
| A2 |  |  |  |  | 3.175% | 0 | 2 | 0 | 0 | 0 | 0 | 2
A1 | A2 |  |  |  |  | 6.349% | 1 | 2 | 0 | 0 | 0 | 0 | 3
|  | A3 |  |  |  | 7.937% | 0 | 0 | 4 | 0 | 0 | 0 | 4
A1 |  | A3 |  |  |  | 11.9% | 1 | 0 | 4 | 0 | 0 | 0 | 5
| A2 | A3 |  |  |  | 12.7% | 0 | 2 | 4 | 0 | 0 | 0 | 6
A1 | A2 | A3 |  |  |  | 14.29% | 1 | 2 | 4 | 0 | 0 | 0 | 7
|  |  | A4 |  |  | 11.11% | 0 | 0 | 0 | 8 | 0 | 0 | 8
A1 |  |  | A4 |  |  | 13.49% | 1 | 0 | 0 | 8 | 0 | 0 | 9 |  |  | A. Individuals are asked to participate in:
| A2 |  | A4 |  |  | 15.87% | 0 | 2 | 0 | 8 | 0 | 0 | 10 |  |  | A.1 Induction
A1 | A2 |  | A4 |  |  | 20.63% | 1 | 2 | 0 | 8 | 0 | 0 | 11 |  |  | A.2 Workshops
|  | A3 | A4 |  |  | 22.22% | 0 | 0 | 4 | 8 | 0 | 0 | 12 |  |  | A.3 Lunch & Learn sessions
A1 |  | A3 | A4 |  |  | 23.02% | 1 | 0 | 4 | 8 | 0 | 0 | 13 |  |  | A.4 Weekly combined talks / meetings
| A2 | A3 | A4 |  |  | 25.4% | 0 | 2 | 4 | 8 | 0 | 0 | 14 |  |  | B. Establishing roles which will promote and support co-evolution
A1 | A2 | A3 | A4 |  |  | 26.98% | 1 | 2 | 4 | 8 | 0 | 0 | 15 |  |  |  | throughout the duration of the project.
|  |  |  | B |  | 20.63% | 0 | 0 | 0 | 0 | 16 | 0 | 16 |  |  | C. Selecting individuals that can operate flexibly in a changing environment
A1 |  |  |  | B |  | 23.81% | 1 | 0 | 0 | 0 | 16 | 0 | 17
| A2 |  |  | B |  | 26.19% | 0 | 2 | 0 | 0 | 16 | 0 | 18 |  |  |  | A1 | A2 | A3 | A4 | B | C
A1 | A2 |  |  | B |  | 28.57% | 1 | 2 | 0 | 0 | 16 | 0 | 19 |  |  | A1 | 10
|  | A3 |  | B |  | 30.16% | 0 | 0 | 4 | 0 | 16 | 0 | 20 |  |  | A2 | 40 | 20
A1 |  | A3 |  | B |  | 33.33% | 1 | 0 | 4 | 0 | 16 | 0 | 21 |  |  | A3 | 90 | 80 | 50
| A2 | A3 |  | B |  | 35.71% | 0 | 2 | 4 | 0 | 16 | 0 | 22 |  |  | A4 | 170 | 160 | 140 | 70
A1 | A2 | A3 |  | B |  | 37.3% | 1 | 2 | 4 | 0 | 16 | 0 | 23 |  |  | B | 350 | 290 | 270 | 220 | 130
|  |  | A4 | B |  | 34.92% | 0 | 0 | 0 | 8 | 16 | 0 | 24 |  |  | C | 630 | 540 | 500 | 460 | 370 | 200
A1 |  |  | A4 | B |  | 36.51% | 1 | 0 | 0 | 8 | 16 | 0 | 25
| A2 |  | A4 | B |  | 37.3% | 0 | 2 | 0 | 8 | 16 | 0 | 26
A1 | A2 |  | A4 | B |  | 41.27% | 1 | 2 | 0 | 8 | 16 | 0 | 27
|  | A3 | A4 | B |  | 42.86% | 0 | 0 | 4 | 8 | 16 | 0 | 28
A1 |  | A3 | A4 | B |  | 40.48% | 1 | 0 | 4 | 8 | 16 | 0 | 29
| A2 | A3 | A4 | B |  | 46.03% | 0 | 2 | 4 | 8 | 16 | 0 | 30
A1 | A2 | A3 | A4 | B |  | 55.56% | 1 | 2 | 4 | 8 | 16 | 0 | 31
[5 empty] | C | 31.75% | 0 | 0 | 0 | 0 | 0 | 32 | 32
A1 |  |  |  |  | C | 34.13% | 1 | 0 | 0 | 0 | 0 | 32 | 33
| A2 |  |  |  | C | 38.1% | 0 | 2 | 0 | 0 | 0 | 32 | 34
A1 | A2 |  |  |  | C | 39.68% | 1 | 2 | 0 | 0 | 0 | 32 | 35
|  | A3 |  |  | C | 43.65% | 0 | 0 | 4 | 0 | 0 | 32 | 36
A1 |  | A3 |  |  | C | 44.44% | 1 | 0 | 4 | 0 | 0 | 32 | 37
| A2 | A3 |  |  | C | 47.62% | 0 | 2 | 4 | 0 | 0 | 32 | 38
A1 | A2 | A3 |  |  | C | 50.79% | 1 | 2 | 4 | 0 | 0 | 32 | 39
|  |  | A4 |  | C | 45.24% | 0 | 0 | 0 | 8 | 0 | 32 | 40
A1 |  |  | A4 |  | C | 48.41% | 1 | 0 | 0 | 8 | 0 | 32 | 41
| A2 |  | A4 |  | C | 49.21% | 0 | 2 | 0 | 8 | 0 | 32 | 42
A1 | A2 |  | A4 |  | C | 51.59% | 1 | 2 | 0 | 8 | 0 | 32 | 43
|  | A3 | A4 |  | C | 53.17% | 0 | 0 | 4 | 8 | 0 | 32 | 44
A1 |  | A3 | A4 |  | C | 57.14% | 1 | 0 | 4 | 8 | 0 | 32 | 45
| A2 | A3 | A4 |  | C | 60.32% | 0 | 2 | 4 | 8 | 0 | 32 | 46
A1 | A2 | A3 | A4 |  | C | 62.7% | 1 | 2 | 4 | 8 | 0 | 32 | 47
|  |  |  | B | C | 58.73% | 0 | 0 | 0 | 0 | 16 | 32 | 48
A1 |  |  |  | B | C | 57.94% | 1 | 0 | 0 | 0 | 16 | 32 | 49
| A2 |  |  | B | C | 61.11% | 0 | 2 | 0 | 0 | 16 | 32 | 50
A1 | A2 |  |  | B | C | 61.9% | 1 | 2 | 0 | 0 | 16 | 32 | 51
|  | A3 |  | B | C | 65.87% | 0 | 0 | 4 | 0 | 16 | 32 | 52
A1 |  | A3 |  | B | C | 66.67% | 1 | 0 | 4 | 0 | 16 | 32 | 53
| A2 | A3 |  | B | C | 68.25% | 0 | 2 | 4 | 0 | 16 | 32 | 54
A1 | A2 | A3 |  | B | C | 77.78% | 1 | 2 | 4 | 0 | 16 | 32 | 55
|  |  | A4 | B | C | 73.02% | 0 | 0 | 0 | 8 | 16 | 32 | 56
A1 |  |  | A4 | B | C | 71.43% | 1 | 0 | 0 | 8 | 16 | 32 | 57
| A2 |  | A4 | B | C | 75.4% | 0 | 2 | 0 | 8 | 16 | 32 | 58
A1 | A2 |  | A4 | B | C | 74.6% | 1 | 2 | 0 | 8 | 16 | 32 | 59
|  | A3 | A4 | B | C | 79.37% | 0 | 0 | 4 | 8 | 16 | 32 | 60
A1 |  | A3 | A4 | B | C | 76.19% | 1 | 0 | 4 | 8 | 16 | 32 | 61
| A2 | A3 | A4 | B | C | 85.71% | 0 | 2 | 4 | 8 | 16 | 32 | 62
A1 | A2 | A3 | A4 | B | C | 100% | 1 | 2 | 4 | 8 | 16 | 32 | 63
Return 2 Qstnr

## SLD1Str
Question SLD1Str
Structural flexibility | [7 empty] | Selection | Communicational flexibility | [6 empty] | Selection
1. Teams within the same discipline are fixed on their task | [7 empty] | FALSE | 11. There is no interaction between the different teams | [6 empty] | FALSE
2. Teams remain in a discipline role throughout the project | [7 empty] | FALSE | 12. Teams do not exchange views / communicate between them | [6 empty] | FALSE
3. Teams remain in a functional role throughout the project | [7 empty] | FALSE | 13. Teams do not know what each other are doing; need to do; will be doing. | [6 empty] | FALSE
4. Project structure is formed on a stage by stage basis – no overlaps | [7 empty] | FALSE | 14. Exchange of views / Communication only happens at Discipline leader level | [6 empty] | FALSE
5. Overlaps are covered by allowing for the older structure to remain in place for a period of time to support the new members that will take the project forward to the next stage | [7 empty] | FALSE | 15. Exchange of views / Communication only happens between Team leaders | [6 empty] | FALSE
6. Assigning roles / identifying individuals to act as Liaison Devices between the teams | [7 empty] | FALSE | 16. Teams know what each other are doing; need to do; will be doing. | [6 empty] | FALSE
7. The project structure is supported by an Organisational Integration role | [7 empty] | FALSE | 17. There is frequent exchange of views between the different teams | [6 empty] | FALSE
8. Team leaders rotate between the same discipline teams | [7 empty] | FALSE | 18. Teams are briefed together on the upcoming tasks and | [6 empty] | FALSE
9. Teams within the same discipline are rotating | [7 empty] | FALSE | 19. Discipline / Teams leaders discuss and resolve together general / project problems | [6 empty] | FALSE
10. Teams decide on the structure they will need (Moore D, 2002 p.183) | [7 empty] | FALSE | 20. Teams discuss and resolve together general / project problems | [6 empty] | FALSE
[7 empty] | 0 | 0 | [6 empty] | 0 | 0
Structural
0
|  | No Flexibility | [10 empty] | Complete Flexibility
| Bullet Point |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| Rank |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Communicational
|  | No Flexibility | [10 empty] | Complete Flexibility
| Bullet Point |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| Rank |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Return 2 Qstnr

## SLD2bStr
Question SLD2bStr
Selection | [16 empty] | 0.015873
A. Individuals are asked to participate in:
A.1 Induction | [16 empty] | TRUE |  |  | 1
A.2 Workshops | [16 empty] | FALSE
A.3 Lunch & Learn sessions | [16 empty] | FALSE
A.4 Weekly combined talks / meetings | [16 empty] | FALSE
B. Establishing roles which will enable and support self-modification throughout the duration of the project. | [16 empty] | FALSE
C. Selecting individuals that can operate flexibly in a changing environment | [16 empty] | FALSE
1
Combination | [5 empty] | Score | [8 empty] | A1 | A2 | A3 | A4 | B | C
0 | [5 empty] | 1.587% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | 10
| 0 |  |  |  |  | 3.175% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A2 | 40 | 20
0 | 0 |  |  |  |  | 6.349% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A3 | 90 | 80 | 50
|  | 0 |  |  |  | 7.937% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A4 | 170 | 160 | 140 | 70
0 |  | 0 |  |  |  | 11.9% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B | 350 | 290 | 270 | 220 | 130
| 0 | 0 |  |  |  | 12.7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | 630 | 540 | 500 | 460 | 370 | 200
0 | 0 | 0 |  |  |  | 14.29% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 11.11% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 0 |  |  | 13.49% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  |  | 15.87% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  | 0 |  |  | 20.63% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 |  |  | 22.22% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 |  |  | 23.02% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 |  |  | 25.4% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  |  | 26.98% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 20.63% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  |  | 0 |  | 23.81% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  |  | 0 |  | 26.19% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 |  | 28.57% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 |  | 0 |  | 30.16% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 |  | 0 |  | 33.33% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 |  | 35.71% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 |  | 0 |  | 37.3% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  | 34.92% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 0 | 0 |  | 36.51% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 | 0 |  | 37.3% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  | 0 | 0 |  | 41.27% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 |  | 42.86% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 |  | 40.48% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | 46.03% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 |  | 55.56% | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 31.75% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  |  |  | 0 | 34.13% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  |  |  | 0 | 38.1% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 39.68% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  | 0 | 43.65% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 |  |  | 0 | 44.44% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  |  | 0 | 47.62% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 50.79% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 45.24% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 0 |  | 0 | 48.41% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 49.21% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  | 0 |  | 0 | 51.59% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 |  | 0 | 53.17% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 |  | 0 | 57.14% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 |  | 0 | 60.32% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 62.7% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 58.73% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  |  | 0 | 0 | 57.94% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  |  | 0 | 0 | 61.11% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 61.9% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 |  | 0 | 0 | 65.87% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 |  | 0 | 0 | 66.67% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 68.25% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 |  | 0 | 0 | 77.78% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 73.02% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 0 | 0 | 0 | 71.43% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 | 0 | 0 | 75.4% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  | 0 | 0 | 0 | 74.6% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 79.37% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 | 76.19% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 85.71% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0
Return 2 Qstnr

## SLD3Sel
A1 | A2 | A3 | A4 | B | C
Question SLD3Sel
Selection | [13 empty] | 0.058824
A. Individuals are asked to participate in:
A.1 Induction | [13 empty] | TRUE | 1
A.2 Workshops | [13 empty] | FALSE
A.3 Lunch & Learn sessions | [13 empty] | FALSE
A.4 Weekly combined talks / meetings | [13 empty] | FALSE
1
Combination | [5 empty] | Score | [10 empty] | A1 | A2 | A3 | A4
A1 | [5 empty] | 5.882% | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | A1 | 10
| A2 |  |  |  |  | 11.76% | 0 | 2 | 0 | 0 | 0 | 0 | 2 |  |  | A2 | 40 | 20
A1 | A2 |  |  |  |  | 23.53% | 1 | 2 | 0 | 0 | 0 | 0 | 3 |  |  | A3 | 90 | 80 | 50
|  | A3 |  |  |  | 29.41% | 0 | 0 | 4 | 0 | 0 | 0 | 4 |  |  | A4 | 170 | 160 | 140 | 70
A1 |  | A3 |  |  |  | 44.12% | 1 | 0 | 4 | 0 | 0 | 0 | 5
| A2 | A3 |  |  |  | 47.06% | 0 | 2 | 4 | 0 | 0 | 0 | 6
A1 | A2 | A3 |  |  |  | 52.94% | 1 | 2 | 4 | 0 | 0 | 0 | 7
|  |  | A4 |  |  | 41.18% | 0 | 0 | 0 | 8 | 0 | 0 | 8
A1 |  |  | A4 |  |  | 50% | 1 | 0 | 0 | 8 | 0 | 0 | 9
| A2 |  | A4 |  |  | 58.82% | 0 | 2 | 0 | 8 | 0 | 0 | 10
A1 | A2 |  | A4 |  |  | 76.47% | 1 | 2 | 0 | 8 | 0 | 0 | 11
|  | A3 | A4 |  |  | 82.35% | 0 | 0 | 4 | 8 | 0 | 0 | 12
A1 |  | A3 | A4 |  |  | 85.29% | 1 | 0 | 4 | 8 | 0 | 0 | 13
| A2 | A3 | A4 |  |  | 94.12% | 0 | 2 | 4 | 8 | 0 | 0 | 14
A1 | A2 | A3 | A4 |  |  | 100% | 1 | 2 | 4 | 8 | 0 | 0 | 15
Return 2 Qstnr

## SLD4cSel
Question: SLD4cSel
Scale |  | Selection | 10
Simply identify resource demand and request allocation of personnel |  | TRUE | 1
Looking at each package (no WBS, or OBS) and identifying team leaders according to their skill and profile |  | FALSE | 0
Looking at each package (no WBS, or OBS) and identifying individuals according to their skill and profile |  | FALSE | 0
Using the RAM as it is derived from the use the WBS / OBS matrix. Identifying down to companies (contractual level) |  | FALSE | 0
Using the RAM as it is derived from the use the WBS / OBS matrix. Identifying down to team leaders and according to their skills |  | FALSE | 0
Using the RAM as it is derived from the use the WBS / OBS matrix. Identifying down to individuals and according to their skills |  | FALSE | 0
Return 2 Qstnr

## SLD4Str
Question: SLD4Str
WBS | Selection | OBS | Selection | 10
Project (Level 0) | TRUE | Director (Level 0) | TRUE | 1 | 1
Work Package Level(n-2) | FALSE | Project Manager (Level n-4) | FALSE | 0 | 0
Components Level(n-1) | FALSE | Discipline Leader (Level n-3) | FALSE | 0 | 0
Job Cards Level(n) | FALSE | Team Leader (Level n-2) | FALSE | 0 | 0
|  | Supervisor (Level n-1) | FALSE |  | 0
|  | Team Member (Level n) | FALSE |  | 0
Return 2 Qstnr

## SLD5bSel
Question: SLD5bSel
Measures to minimise or maximise the effect of mutation |  | Selection | 0
Individuals’ profile is considered when allocated to tasks. (A) |  | FALSE | 0
Selection of team members is supported by personal profiling. (A) |  | FALSE | 0
Individuals’ ambitions are considered when assigned to project tasks and are followed with project as well as company performance development plans. (A) |  | FALSE | 0
Team leaders are knowledgeable of team members’ aspirations and support them in achieving them. (A) |  | FALSE | 0
Individuals have flexibility to carry out their tasks. (A) / (B) |  | FALSE | 0
Team events are organised frequently – celebrating success, setting up and assigning the targets. (B) |  | FALSE | 0
Feedback from individuals is frequently requested. (B) |  | FALSE | 0
Each project team member is kept informed about succession planning (B) |  | FALSE | 0
The effect of destructive disruptions reaching individuals is minimised. (B) |  | FALSE | 0
Disruptive conflict is minimised. (B) |  | FALSE | 0
The PM is setting up project performance development plan that is cascaded down to the lowest levels for all teams. (B) |  | FALSE | 0
Return 2 Qstnr

## SLD5bStr
Question SLD5bStr
Measures to minimise or maximise the effect of mutation |  | Selection | 0
The project structure is reviewed to accommodate the stage requirement(s) |  | FALSE | 0
Teams are kept flexible to allow for innovation when required |  | FALSE | 0
The project structure to be followed is discussed with team leadership |  | FALSE | 0
Task force(s) are set up to address, quickly, issues regarding the project structure as and when these arise |  | FALSE | 0
Return 2 Qstnr

## SLD5Mng
Question: SLD5Mng
Scale |  | Selection | 30
No action(s) |  | FALSE | 0
Building team environment – team events |  | TRUE | 3
Frequent team events, with appropriate awards for various successes |  | FALSE | 0
Management considering consequence of actions and taking necessary corrective, counteractive, pre-emptive actions |  | FALSE | 0
Building close affiliation between team members; Building ‘affiliative leadership’ style (‘Primal Leadership’, Coleman D, et.al., 2002) |  | FALSE | 0
Implementing a number of other EI leadership competencies (App B of above reference) |  | FALSE | 0
Return 2 Qstnr

## SLD7bSel
Question: SLD7bSel
Scale |  | Selection | 0
Detailed team selection process, not just CVs, for:
1. Manager level |  | FALSE | 0
2. Discipline leader level |  | FALSE | 0
3. Team leader level |  | FALSE | 0
4. Supervisor level |  | FALSE | 0
5. Team member level |  | FALSE | 0
Use of personal profiling to identify individuals’ characteristics (Belbin and Myers Briggs) and build the teams |  | FALSE | 0
Use of the organisational effectiveness personnel (or personnel / HR dept) to support individuals and teams throughout the project |  | FALSE | 0
Carry out inter-team personal (between different suppliers) profiling to enable team environment. Follow ups. |  | FALSE | 0
Return 2 Qstnr

## SLB1Mng
Question: SLB1Mng
Project Stage |  | Management Style Click into the cell to select from the drop down list (Values in the table below)
Conception |  | D) Decisions based on standardised processes, procedures and rules. | D | 3
Feasibility |  | E) Emphasis was given to perfection and the technical approach rather than an outcome which satisfies the requirements, thus resulting in less delegation and trust on work done by others. | E | 3
Design |  | J) Emphasis was given to the medium to longer term objectives of the organisation, rather than the immediate needs of the client. | J | 3
Construction |  | E) Emphasis was given to perfection and the technical approach rather than an outcome which satisfies the requirements, thus resulting in less delegation and trust on work done by others. | E | 3
Commissioning |  | E) Emphasis was given to perfection and the technical approach rather than an outcome which satisfies the requirements, thus resulting in less delegation and trust on work done by others. | E | 3
30
Management Style
A) Decisions were made after there had been a discussion with the project team – egalitarian approach. |  |  |  |  | A | 7
B) Decisions and actions to be taken were dictated to the project team with no consultation. |  |  |  |  | B | 1
C) Decisions were made by the teams, who were allowed to manage themselves. |  |  |  |  | C | 10
D) Decisions based on standardised processes, procedures and rules. |  |  |  |  | D | 3
E) Emphasis was given to perfection and the technical approach rather than an outcome which satisfies the requirements, thus resulting in less delegation and trust on work done by others. |  |  |  |  | E | 3
F) The management style varied according to the stages of the project, changing and/or adjusting according to the situation. |  |  |  |  | F | 5
G) Emphasis given to systems of control, efficiency and productivity. |  |  |  |  | G | 1
H) Emphasis was given to project team members’ well-being, their involvement and development rather than your own career progression. |  |  |  |  | H | 7
J) Emphasis was given to the medium to longer term objectives of the organisation, rather than the immediate needs of the client. |  |  |  |  | J | 3
Return 2 Qstnr

## SLB2bSel
A1 | A2 | A3 | A4 | B | C
Question SLB2bSel
Selection | [13 empty] | 0.015873
A. Individuals are asked to participate in: | [14 empty] | 1
A.1 Induction | [13 empty] | TRUE | 1
A.2 Workshops | [13 empty] | FALSE
A.3 Lunch & Learn sessions | [13 empty] | FALSE
A.4 Weekly combined talks / meetings | [13 empty] | FALSE
B. Establishing roles which will promote and support the transformation from homogeneous to self-organising throughout the duration of the project. | [13 empty] | FALSE
C. Selecting individuals that can operate flexibly in a changing environment | [13 empty] | FALSE
Combination | [5 empty] | Score | [10 empty] | A1 | A2 | A3 | A4 | B | C
A1 | [5 empty] | 1.587% | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | A1 | 10
| A2 |  |  |  |  | 3.175% | 0 | 2 | 0 | 0 | 0 | 0 | 2 |  |  | A2 | 40 | 20
A1 | A2 |  |  |  |  | 6.349% | 1 | 2 | 0 | 0 | 0 | 0 | 3 |  |  | A3 | 90 | 80 | 50
|  | A3 |  |  |  | 7.937% | 0 | 0 | 4 | 0 | 0 | 0 | 4 |  |  | A4 | 170 | 160 | 140 | 70
A1 |  | A3 |  |  |  | 11.9% | 1 | 0 | 4 | 0 | 0 | 0 | 5 |  |  | B | 350 | 290 | 270 | 220 | 130
| A2 | A3 |  |  |  | 12.7% | 0 | 2 | 4 | 0 | 0 | 0 | 6 |  |  | C | 630 | 540 | 500 | 460 | 370 | 200
A1 | A2 | A3 |  |  |  | 14.29% | 1 | 2 | 4 | 0 | 0 | 0 | 7
|  |  | A4 |  |  | 11.11% | 0 | 0 | 0 | 8 | 0 | 0 | 8
A1 |  |  | A4 |  |  | 13.49% | 1 | 0 | 0 | 8 | 0 | 0 | 9
| A2 |  | A4 |  |  | 15.87% | 0 | 2 | 0 | 8 | 0 | 0 | 10
A1 | A2 |  | A4 |  |  | 20.63% | 1 | 2 | 0 | 8 | 0 | 0 | 11
|  | A3 | A4 |  |  | 22.22% | 0 | 0 | 4 | 8 | 0 | 0 | 12
A1 |  | A3 | A4 |  |  | 23.02% | 1 | 0 | 4 | 8 | 0 | 0 | 13
| A2 | A3 | A4 |  |  | 25.4% | 0 | 2 | 4 | 8 | 0 | 0 | 14
A1 | A2 | A3 | A4 |  |  | 26.98% | 1 | 2 | 4 | 8 | 0 | 0 | 15
|  |  |  | B |  | 20.63% | 0 | 0 | 0 | 0 | 16 | 0 | 16
A1 |  |  |  | B |  | 23.81% | 1 | 0 | 0 | 0 | 16 | 0 | 17
| A2 |  |  | B |  | 26.19% | 0 | 2 | 0 | 0 | 16 | 0 | 18
A1 | A2 |  |  | B |  | 28.57% | 1 | 2 | 0 | 0 | 16 | 0 | 19
|  | A3 |  | B |  | 30.16% | 0 | 0 | 4 | 0 | 16 | 0 | 20
A1 |  | A3 |  | B |  | 33.33% | 1 | 0 | 4 | 0 | 16 | 0 | 21
| A2 | A3 |  | B |  | 35.71% | 0 | 2 | 4 | 0 | 16 | 0 | 22
A1 | A2 | A3 |  | B |  | 37.3% | 1 | 2 | 4 | 0 | 16 | 0 | 23
|  |  | A4 | B |  | 34.92% | 0 | 0 | 0 | 8 | 16 | 0 | 24
A1 |  |  | A4 | B |  | 36.51% | 1 | 0 | 0 | 8 | 16 | 0 | 25
| A2 |  | A4 | B |  | 37.3% | 0 | 2 | 0 | 8 | 16 | 0 | 26
A1 | A2 |  | A4 | B |  | 41.27% | 1 | 2 | 0 | 8 | 16 | 0 | 27
|  | A3 | A4 | B |  | 42.86% | 0 | 0 | 4 | 8 | 16 | 0 | 28
A1 |  | A3 | A4 | B |  | 40.48% | 1 | 0 | 4 | 8 | 16 | 0 | 29
| A2 | A3 | A4 | B |  | 46.03% | 0 | 2 | 4 | 8 | 16 | 0 | 30
A1 | A2 | A3 | A4 | B |  | 55.56% | 1 | 2 | 4 | 8 | 16 | 0 | 31
[5 empty] | C | 31.75% | 0 | 0 | 0 | 0 | 0 | 32 | 32
A1 |  |  |  |  | C | 34.13% | 1 | 0 | 0 | 0 | 0 | 32 | 33
| A2 |  |  |  | C | 38.1% | 0 | 2 | 0 | 0 | 0 | 32 | 34
A1 | A2 |  |  |  | C | 39.68% | 1 | 2 | 0 | 0 | 0 | 32 | 35
|  | A3 |  |  | C | 43.65% | 0 | 0 | 4 | 0 | 0 | 32 | 36
A1 |  | A3 |  |  | C | 44.44% | 1 | 0 | 4 | 0 | 0 | 32 | 37
| A2 | A3 |  |  | C | 47.62% | 0 | 2 | 4 | 0 | 0 | 32 | 38
A1 | A2 | A3 |  |  | C | 50.79% | 1 | 2 | 4 | 0 | 0 | 32 | 39
|  |  | A4 |  | C | 45.24% | 0 | 0 | 0 | 8 | 0 | 32 | 40
A1 |  |  | A4 |  | C | 48.41% | 1 | 0 | 0 | 8 | 0 | 32 | 41
| A2 |  | A4 |  | C | 49.21% | 0 | 2 | 0 | 8 | 0 | 32 | 42
A1 | A2 |  | A4 |  | C | 51.59% | 1 | 2 | 0 | 8 | 0 | 32 | 43
|  | A3 | A4 |  | C | 53.17% | 0 | 0 | 4 | 8 | 0 | 32 | 44
A1 |  | A3 | A4 |  | C | 57.14% | 1 | 0 | 4 | 8 | 0 | 32 | 45
| A2 | A3 | A4 |  | C | 60.32% | 0 | 2 | 4 | 8 | 0 | 32 | 46
A1 | A2 | A3 | A4 |  | C | 62.7% | 1 | 2 | 4 | 8 | 0 | 32 | 47
|  |  |  | B | C | 58.73% | 0 | 0 | 0 | 0 | 16 | 32 | 48
A1 |  |  |  | B | C | 57.94% | 1 | 0 | 0 | 0 | 16 | 32 | 49
| A2 |  |  | B | C | 61.11% | 0 | 2 | 0 | 0 | 16 | 32 | 50
A1 | A2 |  |  | B | C | 61.9% | 1 | 2 | 0 | 0 | 16 | 32 | 51
|  | A3 |  | B | C | 65.87% | 0 | 0 | 4 | 0 | 16 | 32 | 52
A1 |  | A3 |  | B | C | 66.67% | 1 | 0 | 4 | 0 | 16 | 32 | 53
| A2 | A3 |  | B | C | 68.25% | 0 | 2 | 4 | 0 | 16 | 32 | 54
A1 | A2 | A3 |  | B | C | 77.78% | 1 | 2 | 4 | 0 | 16 | 32 | 55
|  |  | A4 | B | C | 73.02% | 0 | 0 | 0 | 8 | 16 | 32 | 56
A1 |  |  | A4 | B | C | 71.43% | 1 | 0 | 0 | 8 | 16 | 32 | 57
| A2 |  | A4 | B | C | 75.4% | 0 | 2 | 0 | 8 | 16 | 32 | 58
A1 | A2 |  | A4 | B | C | 74.6% | 1 | 2 | 0 | 8 | 16 | 32 | 59
|  | A3 | A4 | B | C | 79.37% | 0 | 0 | 4 | 8 | 16 | 32 | 60
A1 |  | A3 | A4 | B | C | 76.19% | 1 | 0 | 4 | 8 | 16 | 32 | 61
| A2 | A3 | A4 | B | C | 85.71% | 0 | 2 | 4 | 8 | 16 | 32 | 62
A1 | A2 | A3 | A4 | B | C | 100% | 1 | 2 | 4 | 8 | 16 | 32 | 63
Return 2 Qstnr

## SLB3bSel
Question: SLB3bSel
Criteria for Selection |  | Selection
1. Positions that are highly affected are identified:
a. Only up to PM level |  | FALSE | 0
b. Only down to Site Manager level |  | FALSE | 0
c. Down to operative level for certain projects |  | FALSE | 0
2. Selection criteria for specific roles do exist |  | FALSE | 0
3. Processes and individuals are expected to use them |  | FALSE | 0
4. Continuous central support exists |  | FALSE | 0
5. Training is provided |  | FALSE | 0
6. Central support to develop interface management exists |  | FALSE | 0
0
Return 2 Qstnr

## SL . ppt
Project Director
K7
Project Manager
1
|  |  |  | Design Manager | [7 empty] | Construction Manager
|  |  |  | Team Leader - Design Manager | [5 empty] | Team Leader - Site Manager |  |  |  | Team Leader - Site Manager
|  |  | Supervisor - (Design) |  |  |  |  | Supervisor - (Site) |  |  |  | Supervisor - (Site) |  | Supervisor - (Site)
| Team Member | Team Member |  |  | Team Member | Team Member |  |  | Team Member |  | Team Member |  | Team Member |  | Team Member
L1
L2
L3
L4
L5
L6
Please select an Area L1-L6 by clicking one of the yellow boxes and return to Qstnr
Only Director
Only PM Level
Only Design, or only Construction Manager level
Both
Design Only Team leader
Construction Only Team leader
Both
Only Design, or Construction Supervisor level
Both Desigh & Construction
Team Member level